## Sheet1
Portfolio Prioritization of Strategic Initiatives | [6 empty] | Implementation Schedule and Risk Buy Down
Item | Strategic Initiative | Incremental Cost | Expected Risk Removal | Return on Control | Cumulative Cost | Cumulative Expected Risk Removal | Planned Start Date | Duration [months] | Planned End Date | Risk of Exceeding Loss Limit | Surprise Loss | Initiaitive | start | end | LLR | P99
1 | EDR MDE (Zero Trust) | 108000 | 187665 | 73.76% | 108000 | 187665 | 2024-08-16 | 6 | 2025-02-12 | 19% | 54000000 | Current |  | 2025-01-12 | 35% | 60000000
2 | Easy SOC (Zero Trust) | 18000 | 182692 | 915% | 126000 | 370357 | 2024-09-17 | 6 | 2025-03-16 | 14% | 48000000 | EDR MDE (Zero Trust) | 2024-08-16 | 2025-02-12 | 19% | 54000000
3 | Supply Chain Risk Management | 525000 | 1750000 | 233.3% | 651000 | 2120357 | 2024-11-18 | 6 | 2025-05-17 | 6.5% | 39000000 | Easy SOC (Zero Trust) | 2024-09-17 | 2025-03-16 | 14% | 48000000
4 | Security Development Lifecycle | 415000 | 1000000 | 141% | 1066000 | 3120357 | 2024-12-19 | 6 | 2025-06-17 | 3% | 25000000 | Supply Chain Risk Management | 2024-11-18 | 2025-05-17 | 6.5% | 39000000
5 | SaaS Apps Risk Management | 145000 | 230000 | 58.62% | 1211000 | 3350357 | 2025-02-20 | 6 | 2025-08-19 | 2% | 21000000 | Security Development Lifecycle | 2024-12-19 | 2025-06-17 | 3% | 25000000
[12 empty] | SaaS Apps Risk Management | 2025-02-20 | 2025-08-19 | 2% | 21000000
| Total | 1211000 | 3350357 | 176.7%
[13 empty] | 45490 | 45902
Formulas:
Planned End Date = Sheet1!$[Planned Start Date]+Sheet1!$[Duration [months]]*30
start = [Planned Start Date, row above]
end = [Planned End Date, row above]